## Sheet1
Task Name | Description | Start Date | End Date | Duration (days)
Test Strategy Definition | Define the overall testing strategy, including objectives, scope (in-scope and out-of-scope items), success criteria, and exit conditions, based on ISTQB standards. | 2025-02-20 | 2025-03-05 | 10
Resource Estimation and Scheduling | Estimate the required testing resources (e.g., personnel, equipment) and develop a realistic schedule that aligns with project deadlines following ISTQB best practices. | 2025-03-06 | 2025-03-10 | 5
Risk Assessment and Mitigation Planning | Identify potential risks related to security, performance, and usability. Develop mitigation strategies and contingency plans in line with ISTQB standards. | 2025-03-11 | 2025-03-15 | 5
Functional Testing | Develop test cases to cover the functional requirements of the system, including data flow and component breakdown. | 2025-03-16 | 2025-04-01 | 15
Integration Testing | Test the integration of components, including the frontend and backend, to ensure seamless interaction. | 2025-04-02 | 2025-04-06 | 5
User Acceptance Testing | Conduct user acceptance testing with end-users to ensure the system meets their expectations. | 2025-04-07 | 2025-04-12 | 6
Error Handling and Validation Testing | Test error handling scenarios, including file format validation, missing data, and file size handling. | 2025-04-13 | 2025-04-17 | 5